## Sheet1
Eventure Jeddah Project Estimate
WBS Items | # Units/Hrs. | Cost/Unit/Hr. (USD) | Subtotals (USD) | WBS Level 1 Totals (USD) | % of Total
1. Project Management |  |  |  | 18600 | 14%
1.1 Project Manager | 240 | 70 | 16800
1.2 Planning & Coordination Tools (Jira/MS Project) | 3 | 200 | 600
2. UI/UX Design |  |  |  | 9300 | 7%
2.1 Bilingual UI Designer | 180 | 50 | 9000
2.2 Design Software Licenses (Figma Pro) | 1 | 300 | 300
3. Development |  |  |  | 62700 | 48%
3.1 Frontend Developer (iOS/Android Hybrid) | 400 | 60 | 24000
3.2 Backend Developer (APIs + Admin Panel) | 400 | 75 | 30000
3.3 Third-Party Services (e.g., Maps API, Calendar API) | 1 | 600 | 600
4. Infrastructure |  |  |  | 1350 | 1%
4.1 AWS Cloud Hosting + Storage | 6 | 200 | 1200
4.2 Domain & SSL | 1 | 150 | 150
5. Testing & QA |  |  |  | 10175 | 8%
5.1 QA Engineer (manual testing) | 150 | 45 | 6750
5.2 Device Testing Access | 1 | 800 | 800
6. Marketing & Support |  |  |  | 3500 | 3%
6.1 Launch Campaign | 1 | 2500 | 2500
6.2 User Support/Helpdesk Setup | 1 | 1000 | 1000
7. Contingency (14.96%) |  |  |  | 37300 | 15%
Total Estimated Cost |  |  | 37300 | 130000 | 100%

## Sheet2
* Software development | #Units/Hrs | Cost/ units /Hr | Subtotal | Calculations
Contractor labor estimate | 800 | 70 | 56000 | 800*$70
Project team member estimate | 600 | 65 | 39000 | 600*65
Total labor estimate |  |  | 95000 | Sum above
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 4 | 4 | 16 | 4*4
External interface files | 3 | 6 | 18 | 3*6
External outputs | 3 | 5 | 15 | 3*5
External queries | 2 | 3 | 6 | 2*3
Logical internal tables | 5 | 8 | 40 | 5*8
Total function points |  |  | 95 | Sum above
Java 2 languange equivalency |  |  | 46 | Assume reference
Source lines of code (SLOC) estimate |  |  | 4370 | 95*46
Productivity *KSLOC^Penalty (person months) |  |  | 28.3 | See reference
Total labor hours (160 hours/month) |  |  | 4528 | 160*28.3
Cost/labor hour |  |  | 7.72 | 130,000$/16,830
Total software development estimate |  |  | 130,000$ | Based on adjusted budget cap